## Requirements
SN | Functionality | Details | User Input (Buttons)
1 | Login Page (SSO) | User can enter their credentials. Authentication will be done from the DNB AD. If autentication success, then Home page will be shown else, error message will be shown. | Login Cancel
2 | Home Page (Search Page) | Home Page will have two text boxes - Customer Name and Mobile No. and two buttons. User can enter Name and/or Mobile No and click on Search button. Search will return the Customer record if found else, error message will be shown. Also this page will have Logout button to logout from the application | Search Logout
3 | Customer Page (Result) | If the search found Customer record, those customer details will be populated in the Customer Page. And four buttons will be shown. 1) Export to Excel - Displayed Customer details will be exported to Excel and prompted for excel file name. 2) Delete Customer - This will delete the Customer record shown on the Customer page from the database permanently. 3) New Search - This will leads the user to Home Page. 4) Logout - Logout from the application. | Export to Excel Delete Customer New Search Logout
3.1 | Rest API for record retrieval | Rest API Service will be triggered to search the customer record from the database and return the results back to API.
3.2 | Export to Excel | Export the Customer details to Excel.
3.3 | Delete Record | Delete the Customer record from the Database.
4 | Job to Delete Records | SQL job will run once in a day at the scheduled time to delete the Customer records older than 10 years. Systems today date will be compared with Customer Created Date.

## Project Plan
SN | Task Name | Duration (Days) | Start | Finish | Owner | Status | Remarks
1 | Login Page (SSO) Development | TBD
2 | Home Page (Search Page) Development | 11
3 | Customer Page (Result) Development | 2
3.1 | Rest API service development | 0 |  |  |  |  | Effort included in SN.2
3.2 | Export to Excel functionality development | 3
3.3 | Delete Record functionalilty development | 2
4 | Job to Delete Records development | 1
19

## Dependencies
SN | Pre-requisites/ Dependencies | Owner | Status | Remarks
1 | ABID Creation for Thiru | Raghu / Ashish | Completed
2 | PAABID Creation for Thiru | Raghu / Ashish | Completed
3 | Access on the servers for Thiru | Raghu / Ashish | Completed
4 | RSA Token for Thiru | Raghu / Ashish | In Progress
5 | SoW Screenshots / PO | Ashish | In Progress | This is required to initiate Seat allocation process
6 | Database backup on the development server | Ashish | In Progress
7 | Required software in development server | Ashish | In Progress | List of required software has been shared
8 | ABID Creation for Aravindh | Raghu / Ashish | To be Started
9 | PAABID Creation for Aravindh | Raghu / Ashish | To be Started
10 | Access on the servers for Aravindh | Raghu / Ashish | To be Started
11 | RSA Token for Aravindh | Raghu / Ashish | To be Started

## Sheet2
Deliverables
1 | Requirement Document
Wireframe/flow chart
2 | Project Plan with Efforts | Internal
3 | Design Document
Desktop for Abith