## Project Plan
SN | Task Name | Duration (Days) | Start | Finish | Owner | Status | Remarks
1 | Login Page (SSO) Development | 2
2 |  | 11
3 | Customer Page (Result) Development | 2
3.1 | Rest API service development | 0 |  |  |  |  | Effort included in SN.2
3.2 | Export to Excel functionality development | 3
3.3 | Delete Record functionalilty development | 2
4 | Job to Delete Records development | 1
21
| Home Page (Search Page) UI Design |  | 21/2 | 21/2 | Abith
| Home Page (Search Page) functionality (Rest API) |  | 21/2 | 26/2 | Aravinth
| Customer Page UI Design |  | 25/2 | 25/2 | Abith
| Customer Page functionality |  | 27/2 | 27/2 | Aravinth
| Export to Excel functionality development |  | 28/2 | 1st Mar | Abith, Aravinth
| Button Delete functionality |  | 1st Mar | 1st Mar | Aravinth