## Project Plan
SN | Task Name | Duration (Days) | Start | Finish | Owner | Status | Remarks
1 | Login Page (SSO) Development | 2 | 2019-02-18 | 2019-02-20
2 | Home Page (Search Page) Development | 11 | 2019-02-21 | 2019-03-06
3 | Customer Page (Result) Development | 2 | 2019-03-07 | 2019-03-11
3.1 | Rest API service development | 0 | 2019-03-12 | 2019-03-12 |  |  | Effort included in SN.2
3.2 | Export to Excel functionality development | 3 | 2019-03-13 | 2019-03-18
3.3 | Delete Record functionalilty development | 2 | 2019-03-19 | 2019-03-21
4 | Job to Delete Records development | 1 | 2019-03-22 | 2019-03-25
21
Formulas:
Finish = [Start]+[Duration (Days)]
Finish = [Start]+[Duration (Days)]+2
Start = [Finish, row above]+1